ANR-BBSRC SysBio 2007 ANR-BBSRC COLLABORATIVE PROPOSALS IN SYSTEMS BIOLOGY

Second Biannual Progress Report

July-December 2008

The aim of this document is to provide a means for reporting the progress of the ten projects funded under this initiative. The form should be completed by the Project Coordinator, with input from all partners. Progress reports will be submitted every six months according to the following guidelines:

| No. | Modality | Reporting Period | Deadline |
| --- | --- | --- | --- |
| 1 | Progress Report | 0-6m | No later than 3 months after each 6-monthly period is completed. |
| 2 |  | 6-12m |  |
| 3 |  | 12-18m |  |
| 4 |  | 18-24m |  |
| 5 |  | 24-30m |  |
| 6 | Final Report | 0-36m | No later than 3 months after the completion of the project. |

Progress reports must be submitted by e-mail to the ANR and BBSRC Secretariats. BBSRC grant holders must submit their Final Report following the BBSRC guidelines.

ANR

Dr. Véronique Briquet-Laugier

Département Biologie Santé

ANR, Agence Nationale de la Recherche

212, rue de Bercy

75012 Paris France

e-mail: veronique.briquet-laugier@agencerecherche.fr

BBSRC

Dr. Gabriela Pastori

Science and Technology Group

BBSRC, Biotechnology and Biological Sciences Research Council

Polaris House, North Star Avenue

Swindon, Wilts SN2 1UH United Kingdom

e-mail: gabriela.pastori@bbsrc.ac.uk

A. Identification

| Programme – Year | ANR-BBSRC SYSBIO 2007 |
| --- | --- |
| Project Title | Olfactory coding in the insect pheromone pathway: models and experiments |
| Short Title | PHEROSYS |
| Project Coordinator Laboratory/Research Organisation | Jean-Pierre Rospars, UMR 1272 (PISC)/INRA |

| Project Partner(s) | Laboratory/Research Organisation, Country |
| --- | --- |
| - Jean-Pierre Rospars | UMR 1272 Physiologie de l’Insecte, INRA, France |
| - Dominique Martinez | Equipe CORTEX, LORIA, France |
| - Thomas Nowotny | CCNR, University of Sussex, UK |

| Decision reference | ANR-BBSRC 07 BSYS 006 |
| --- | --- |
| Starting Date | January 1st, 2008 |
| Reporting Period | Second semester 2008 |
| Report written by | Jean-Pierre Rospars |
| Phone | +33 1 30 83 33 55 |
| Email address | rospars@versailles.inra;fr |
| Date | 03 July 2008 |

B. Work progress

Please describe briefly the status of each task/objective.

| Tasks/Objectives | 2008 |  | 2009 | 2010 | Comments (if necessary) |
| --- | --- | --- | --- | --- | --- |
|  | + 6 Months | +12 months |  |  |  |
| D1.1 RP generation (task 1a) |  |  |  |  |  |
| D1.2 MGC organization (task 1c) |  |  |  |  |  |
| D1.3 Model of sensillum (task 1a) |  |  | Δ |  |  |
| D1.4 ORN message (task 1b) |  |  | Δ |  |  |
| D1.5 Fine MGC organization (1c) |  |  | Δ |  |  |
| D1.6 ORN message freq (task 1b) |  |  |  | Δ |  |
| D1.7 Pheromone delivery (new task) | ▲ |  |  |  |  |
| D2.1 Single neuron model (task 2a) |  |  | Δ |  | Delayed |
| D2.2 Detailed one-glom model (2a) |  |  | Δ |  | Delayed |
| D2.3 Simplified one-glom model (2a) |  |  |  | Δ |  |
| D2.4 Amplification (task 2b) |  |  | Δ |  |  |
| D2.5 Noise suppression (task 2b) |  |  | Δ |  |  |
| D2.6 Intermittent stimuli (task 2c) |  |  |  | Δ | Delayed |
| D3.1 MGC model (task 3a) |  |  | Δ |  |  |
| D3.2 Simple model (task 3a) |  |  | Δ |  |  |
| D3.3 LN inhibition (task 3d) |  |  | Δ |  |  |
| D3.4 Emergence of oscillations (3d) |  |  | Δ |  | Delayed |
| D3.5 Role of oscillations (task 3c) |  |  |  | Δ | Delayed |
| D3.6 Role of inhibition (task 3d) |  |  |  | Δ |  |

| Δ | Foreseen | ▲ | New |  | Abandoned |   | Completed In progress |
| --- | --- | --- | --- | --- | --- | --- | --- |

C. Short description of the project and milestones (half page max) – please give details of the progress achieved against your overall objectives, list the main achievements and outputs of your collaborative project.

1. WP1: Antennal input to the antennal lobe.

Task 1a. Single ORN organization (INRA). Experiments: Analysis of the stimulus delivery, based on radiochemical experiments and modelling, has been abandoned (see D.3 below). Modelling: The paper on the detailed biophysical model of receptor potential generation has been achieved. It is now accepted in a journal with a relatively high (6.5) IF [P3]. A complete sensillum model has been developed and a first draft paper has been written [D1].

Task 1b. Population of ORNs (INRA). Experiments: In vivo recordings of olfactory receptor neurons (ORNs) are being performed in order to determine their latency, threshold, dynamic range, maximum firing frequency etc. Modelling: A paper predicting the global properties of the ORN population has been written and submitted [S1]. It is now under revision.

Task1c. Projection of ORNs and MGC organization (INRA). Anatomical investigations of the macroglomerular complex (MGC) has been achieved in the context of a global quantitative analysis of the glomerular organization of the antennal lobe. A paper has been submitted  [S2] which is now under review. Investigations of the ORN and PN projections into the MGC have been achieved and a first draft paper has been written [D2].

2. WP2: Single glomerulus.

Task 2a. PN and LN response patterns. At INRA: The paper on in vivo intracellular recording of projection neurons (PNs) and their responses to pheromone components has just been accepted for publication [P2]. At CCNR: A convergent model for the single glomerulus has been formulated – so far with generic neuron models which can be replaced by specific models later.

Task 2b. Amplification. At INRA: The analysis of recordings of ORNs (1a) and PNs (2a) is now in progress to characterize the ORN-to-PN conversion, especially their amplification properties. At CCNR: Dr. Buckley has begun to analyze general properties of convergent neuronal networks and their ability to enhance signal-to-noise ratios. Based on the data from Bombyx mori in the literature, our preliminary results seem to indicate that convergence on its own is not able to explain the observed behavioral performance. Refinements of this result and the investigation of alternative (or additional) mechanisms to increase sensitivity and specificity are under way.

Task 2c. Temporal structure (INRA, LORIA). The recordings from PNs (2a and 3a) show a definite inhibition phase. We are studying the possibility to determine its origin (intrinsic or extrinsic) by using current injections and drugs (see also 3b).

3. WP3: Several glomeruli.

Task 3a. Neural network organization. At INRA: Dr Chaffiol has succeeded to solve a major difficulty mentioned in our First Report: the extracellular recordings from antennal lobes. This is a significant progress. Now gathering of a large sample of such recordings is under way. At CCNR: Dr. Zavada has assembled a first Hodgkin-Huxley-based 2-glomerulus model. The specificity of the system to pheromone blends of a specific ratio of components has been reproduced over a 10 fold range of concentrations. First results have been presented at the BBSRC conference [C3] and further developments will be shown at the Cosyne conference 2009, Salt Lake City. At LORIA: detailed and simplified models of the MGC based on data from the literature are being studied. The role of inter-glomerular connections in encoding the pheromone blend in the integrate-and-fire network model tuned to experimental results described in the First Report have now been investigated [C2].  We have started to study the corresponding random network.

Tasks 3b, c, d. Oscillations & synchronization. At LORIA: putative complementary roles of GABA-A and –B inhibition in synchronizing/desynchronizing PNs have been analyzed theoretically [P1]. At INRA: experimental difficulties are encountered on recording local field potential oscillations (see D.4). On the basis of experiments in progress (3a) we are preparing experimental tests with GABA antagonists of predictions (complementary roles for GABA-A and B inhibition).

4. See the website of the project http://www.informatics.sussex.ac.uk/research/projects/ PheroSys/ for further public information.

### D. Changes to the project (half page max) – please inform of any changes to the project that could affect the completion of tasks/objectives, and of any difficulties/problems encountered with the scientific work, staff or resources. Please summarise your action plan to solve these issues.

1. We have encountered major administrative difficulties with Dr Shereen El Bana who started to work only at the beginning of August. Following an error at the French Consulate in Egypt she came with a wrong visa. Despite repeated attempts of the various administrations in charge of foreign scientists, it proved impossible to have this error corrected in time at the consulate or at the Préfecture in Versailles. Dr El Bana returned to Egypt at the end of January after 6 months without completing the scheduled experiments. Hiring a new postdoc on the same subject is not realistic given the few (6) remaining months available. We are now discussing how to adapt to this situation. Part of Dr El Bana work will be pursued by a recently recruited scientist, Dr N. Dezig (see also item 4 below).

2. There were delays in hiring for the Sussex team. Dr. Andrei Zavada started only 14 May 2008, whereas Dr. Christopher Buckley started only in December. These explain that several projects at CCNR are delayed by 6 months to one year.

3. We have abandoned the project of determining the actual number of pheromone molecules delivered to the preparation. The problem comes from the relatively low specific activity of the radio-labelled pheromone molecules used, so that the total activity of the released molecules is too low for reliable measurements. Commercially available molecules with higher activity are too expensive. Although frustrating this failure is of minor importance for the whole project.

4. The extracellular recordings of local field potentials and the intracellular recordings from local neurons in the antennal lobe proved difficult. Dr El Bana’s resigning complicates this issue.

### E. Deliverables (half page max) – please include publications related to your ANR-BBSRC SysBio project, presentations (talks and posters) at conferences, patents/applications for patents, and attraction of additional funding.

Conferences

[C1] Gu Y., Lucas P., Rospars J.-P. (2008) Modelling the moth pheromone transduction cascade from molecular level to sensillar level. ECRO (European Chemoreception Research Organization), Portoroz, Slovenia, 3-7 September 2008. Abstract N° 109 (poster).

[C2] Bel Mabrouk H., Rospars J.-P., Ezzine J., Martinez D. (2008) Rôle de l’inhibition intra et inter glomérulaire dans la synchronisation neuronal et le codage phéromonal chez Manduca Sexta. Second French Conference in Computational Neurosciences (Neurocomp2008), Marseille, 8-11 October 2008. Paper #59 (poster). Cf. http://hal.archives-ouvertes.fr/ neurocomp08/.

[C3] Zavada A., Martinez D., Rospars J.-P., Nowotny T. (2008) A neuronal network model for the detection of binary odour mixtures, poster. ISB grant holder conference, Nottingham 2008.

[C4] Rospars J.-P., Nowotny T., Martinez D. (2008) Olfactory Coding in the Insect Pheromone Pathway. ISB grant holder conference, Nottingham 2008.

- Articles published or accepted for publication

[P1] Martinez D., Montejo N. (2008) A model of stimulus-specific neural assemblies in the insect antennal lobe. PLoS Computational Biology, vol. 4 (8) August 2008. Cf. http://www.ploscompbiol.org/article/info:doi/10.1371/journal.pcbi.1000139.

[P2] Jarriault D., Gadenne C., Rospars J.-P., Anton S. (2009) Quantitative analysis of projection neuron responses to sex pheromone in the moth Agrotis ipsilon: a tool to study network plasticity. J. Exp. Biol. (accepted in January 2009)

[P3] Gu Y., Lucas P., Rospars J.-P. (2009) Model of the transduction cascade in the moth olfactory receptor neuron sensitive to the sexual pheromone. PLoS Computational Biology (accepted in February)

Articles submitted

[S1] Sandström M., Lansner A., Hellgren-Kotaleski J., Rospars J.-P. (2008) Modeling the response of a population of olfactory receptor neurons to an odorant. J. Comput. Neurosci. (submitted June 2008, revision in progress).

[S2] Couton L., Minoli S., Kiêu K., Anton S., Rospars J.-P. (2008) Constancy and variability of identified glomeruli in the antennal lobes: Computational approach in Spodoptera littoralis. J. Comp. Neurol. (submitted December 2008).

Drafts of articles

[D1] Gu Y. and Rospars J.-P. (2009) A dynamical model of the moth pheromone-sensitive sensillum.

[D2] Couton L., Jarriault D., Rospars J.-P., Anton S. (2009) Identifying pheromone-processing glomerui in Agrotis ipsilon (Lepidoptera: Noctuidae).

F. Staff employed/trained on the project - please give details of interdisciplinary training and career prospects beyond project completion, e.g. tenure position, private industry, unemployment, etc.

| Name | Qualifications | Start date | Length of the contract (months) | Training/Career prospects |
| --- | --- | --- | --- | --- |
| Antoine CHAFFIOL | Postdoc | 1 March 2008 | 18 months | Postdoc abroad |
| Andrei ZAVADA | Postdoc | 14 May 2008 | 24 months | Postdoc |
| Christopher L. BUCKLEY | Postdoc | 1 December 2008 | 28 months | Lecturer |
| Hana BEL MABROUK | Engineer | 1 April 2008 | 33 months | Postdoc |

G. Other staff associated to the project

| Name | Qualifications | Start date | Length of the contract (months) | Training/Career prospects |
| --- | --- | --- | --- | --- |
| Shereen EL BANA | Postdoc | 21 July 2008 | 12 months | Tenured position |
| Alexandre GREMIAUX | Doctoral student | 1 October 2008 | 36 months | Postdoc |
| David JARRIAULT | Doctoral student | 1 October 2007 | 36 months | Postdoc |

H. Financial progress - for each team, please indicate the percentage of budget spent.

| Partner | Consumables (%) | Equipment (%) | Travel & Subsistence |
| --- | --- | --- | --- |
| J.-P. Rospars (INRA) | 4.5% | 20% | -- |
| D. Martinez (LORIA) | 100% | 71% | 9% |
| T. Nowotny (U. Sussex) | 3.9 % | 100 % | 7 % |
|  | Total 12% | Total 36% | Total 8% |

###### I. Reserved for the project coordinator (half page max) – please comment briefly on the management and integration of your project, i.e., efficiency, reporting, quality management, communication between participants, project meetings. During the second semester of the project, the main emphasis was on training the newly hired students and postdocs and exploiting systematically the experimental protocols developed in the first semester. Results have been obtained on several aspects of the project (see section E) which are being used as a basis for work in collaboration by the 3 teams of the project. Interactions between the different partners worked very well. Dr Martinez was half-time at INRA to supervise the experiments by Dr Chaffiol and Dr El Banna and to discuss modelling issues with Dr Rospars. A meeting of the 3 groups took place at INRA (22-24 October 2008). Dr Nowotny went again to INRA (22-23 January 2009) to participate to two Thesis Committees (H. Bel Mabrouk and A. Grémiaux) and installing a computer-controlled device for injecting currents (see 2c). It gave us the opportunity to discuss the on-going investigations and most urgent needs. A third meeting of the three partners with collaborators and postdocs will be organized in mid-2009.

J. Any other comments (max. 500 characters)

The relatively low percentage of INRA budget spent in 2008 results from three facts: (1) Purchase of the equipment needed was scheduled for 2009; it is under final negotiation with providers. (2) Most consumables will be likely purchased on other grants obtained after Pherosys was submitted; we are considering a reassignment of part of this budget line on equipment and postdocs. (3) All Pherosys meetings in 2008 have taken place at INRA.

The delay in hiring and other difficulties with postdocs (see D.1 and D.2) has entailed delays in the research program. An extension of at least 6 months in 2011 will be necessary for achieving the expected goals.